## Document_Control
Document Control
Document Title | Change Impact Analysis — spo2-ai-eval-pipeline
Document Version | 1.0
Device/Software Version | SpO2 AI Eval Pipeline v2.1
Date Generated | 2026-04-28
QMS Document Number
SOP Reference
Related Design Controls File
Related Risk Management File
Approval Signatures
Role | Name | Date | Signature
Prepared By
Reviewed By (QA)
Approved By (Management)
Approved By (Regulatory)

## Change_Request
CR ID | Description | Files Changed | Rationale | Date | Requestor
CR-001 | Introduce new emergency classification tier for SpO2 readings below 80%. Currently system only classifies normal/borderline/urgent. Emergency tier triggers immediate page. | src/rules/classifier.py, src/pipeline/orchestrator.py, src/interop/hl7_messages.py, app/components/trace_viewer.py | Clinical safety review identified gap in handling critical desaturation events below 80% SpO2 | 2026-04-28 | Clinical Safety Team
Total CRs:

## Impact_Trace
Changed File | Affected DI IDs | Affected HAZ IDs | Affected VER IDs | Notes
src/rules/classifier.py | DI-001 (classification), DI-002 (desat detection) | HAZ-001 (misclassify urgent) | VER-001, VER-002 | Core classification logic modified to add emergency tier
src/pipeline/orchestrator.py | DI-001 (classification) | HAZ-001 (misclassify urgent) | VER-001 | Pipeline routing updated for new tier
src/interop/hl7_messages.py | DI-003 (handoff reports) | HAZ-005 (handoff context) | VER-003 | HL7 message templates updated for emergency tier
app/components/trace_viewer.py | DI-003 (handoff reports) | — | VER-003 | UI display updated (no direct safety impact)
Total Affected Files:
Affected Items (non-empty):

## Reverification_Scope
VER ID | Test Name | Rationale | Effort Estimate | Priority
VER-001 | Urgency classification test suite | Classification logic changed | 4 hours | P1
VER-002 | Desaturation detection accuracy | New threshold added | 2 hours | P1
VER-003 | Handoff report completeness | New tier in report output | 1 hour | P2
Total Verifications:

## Regulatory_Assessment
Field | Value
Classification | Critical
Pathway | Regulatory review required — likely new 510(k) or Letter to File with extensive V&V
Rationale | Adds new safety-critical classification tier (emergency) that triggers immediate clinical action (page). New clinical decision point affecting patient safety. Per FDA guidance: new risk control implementation in safety-critical pathway. If device has cleared predicate, formal 510(k) equivalence assessment required to determine if new submission needed.
New 510(k) Required | Requires assessment — see Regulatory_Assessment
Risk Analysis Update Required | Yes — add HAZ for emergency tier misclassification
Cumulative Impact Notes | First major change since initial release. No cumulative threshold concern.
510(k) Equivalence Assessment
Predicate Device | N/A — portfolio demonstration project
Predicate Intended Use | N/A
Performance Claims Affected | N/A — no cleared predicate
Substantial Equivalence Conclusion | N/A
Evidence Required | Full system V&V including emergency tier classification accuracy, alarm latency testing, clinical workflow validation