## Document_Control
Document Control
Document Title | Design Review Package — CDR — SpO2 AI Eval Pipeline v2.1
Document Version | 1.0
Device/Software Version | SpO2 AI Eval Pipeline v2.1
Date Generated | 2026-04-28
Review Type | CDR -- Critical Design Review
QMS Document Number
SOP Reference
Related Design Controls File
Related Risk Management File
Approval Signatures
Role | Name | Date | Signature
Prepared By
Reviewed By (QA)
Approved By (Management)

## Review_Summary
Field | Value
Review Type | CDR -- Critical Design Review
Device Name | SpO2 AI Eval Pipeline v2.1
Date | 2026-04-28
Gate | Detailed Design -> Implementation/V&V
Focus | Is the design complete enough to build?
Attendees | [PM Name] (PM), Dr. Chen (Clinical), Sarah Kim (QA/Regulatory), Alex Rivera (Data Science), Jordan Park (Engineering), Independent Reviewer TBD
Overall Completeness
Recommendation

## Artifact_Checklist
Artifact | Required | Provided | Completeness %
OVERALL
1. User needs document complete | Y | Y
2. Design inputs derived from user needs | Y | Y
3. Intended use statement defined | Y | Y
4. User population characterized | Y | Y
5. Use environment described | Y | Y
6. Regulatory pathway identified | Y | Y
7. Applicable standards listed | Y | Y
8. Risk management plan created | Y | Y
9. Initial hazard analysis performed | Y | Y
10. SW safety classification determined | Y | Y
11. System architecture defined | Y | Y
12. Key algorithms identified | Y | Y
13. Data flow documented | Y | Y
14. Interface specifications drafted | Y | Y
15. Performance requirements specified | Y | Y
16. Security requirements identified | Y | Y
17. Privacy/HIPAA assessment done | Y | Y
18. V&V strategy outlined | Y | Y
19. Clinical evidence plan (if needed) | Y | Y
20. Development timeline realistic | Y | Y
21. Resource plan adequate | Y | Y
22. Previous review actions closed | Y | Y
23. Design history file initiated | Y | Y
24. Configuration management set up | Y | Y
25. Supplier/third-party assessment (if applicable) | Y | Y
26. Detailed design specifications complete | Y | Y
27. All design inputs have corresponding outputs | Y | Y
28. Traceability matrix complete (UN->DI->DO->VER->VAL) | Y | Y
29. Design inputs are unambiguous, complete, non-conflicting, and have measurable acceptance criteria (per FDA 820.30(c)) | Y | Y
30. Risk analysis updated with design details | Y | Y
31. All unacceptable risks have control measures | Y | Y
32. Risk controls traced to requirements | Y | Y
33. V&V protocols written and reviewed | Y | Y
34. Test environment specified | Y | Y
35. Acceptance criteria quantified | Y | Y
36. Algorithm performance targets set | Y | Y
37. Data quality requirements defined | Y | Y
38. Integration test plan complete | Y | Y
39. Regression test strategy defined | Y | Y
40. Cybersecurity analysis complete | Y | Y
41. Labeling/IFU drafted | Y | Y
42. Manufacturing/deployment plan drafted | Y | Y
43. Training materials outlined | Y | Y
44. Post-market surveillance plan initiated | Y | Y
45. All CDR action items from PDR closed | Y | N
46. Independent review of critical safety items | Y | Y
47. Biocompatibility assessment (if applicable) | Y | N
48. Electrical safety assessment (if applicable) | Y | N
49. EMC assessment (if applicable) | Y | N
50. Software of Unknown Provenance (SOUP) list complete | Y | Y
51. SBOM (Software Bill of Materials) generated | Y | Y
52. Usability engineering file initiated | Y | Y
53. Clinical evaluation report drafted | Y | N
54. Regulatory submission timeline set | Y | N
55. Budget and resource reconfirmed | Y | N
56. Stakeholder sign-off on design direction | Y | N

## Requirements_Status
Metric | Value
Total User Needs | 5
Total Design Inputs | 5
Total Requirements | 10
Verified | 5/5
% Verified | 100%
Validated | 4/5
% Validated | 80%
Open Items | 1
Open Item Detail | VAL-005 (expert queue routing) pending

## Risk_Status
Metric | Value
Total Hazards Identified | 5
Unacceptable Remaining | 0
ALARP (with rationale) | 2
Acceptable | 3
Open Risk Controls | 0

## Sign_Off
Role | Name | Date | Approval | Notes
PM | [PM Name] | 2026-04-28 | Approve
Clinical Reviewer | Dr. Chen | 2026-04-28 | Conditional | Pending VAL-005 expert queue validation
Data Scientist | Alex Rivera | 2026-04-28 | Approve
QA/Regulatory | Sarah Kim | 2026-04-28 | Conditional | Need regulatory submission timeline
Engineering Lead | Jordan Park | 2026-04-28 | Approve
Independent Reviewer | TBD |  | Pending